# 2WW Colorectal Pathway Audit — Project Log

Project: Concordance audit of an algorithmic decision-support tool for the George Eliot Hospital 2-week-wait lower-GI pathway

Lead: Mr Kasun Wanigasooriya · Project team: Ali Mohamed Elhassan, Lucy-Ann O'Kane, Temitope Ken-Afolabi, Sharanya Arun, Olivia Jackson

Tool: https://ww-colerectal.web.app/audit/new · Data: Teams → 2WW LGI Pathway → "AI 2WW Project" → `2WW-Colorectal-Audit.xlsx`

This log records what has been built and decided, in order, so the team and the audit department can see exactly what was done and when.

# May–June 2026 — Algorithm and tool development

Triage algorithm written for the 2WW lower-GI pathway (current version GEH-2WW-COLORECTAL v0.4.0), encoding the referral criteria and investigation recommendations as explicit, testable rules.

Algorithm covered by 95 automated unit tests, all passing — every rule change re-runs the full test set before deployment.

Web tool built around the algorithm (case details in → recommendation out) for use alongside normal clinical judgement; the algorithm never replaces the clinician's decision.

# 29 June 2026 — Hosting, safety controls, and audit design

Tool moved to Firebase Hosting, UK (London) region, owned and administered by the project.

Patient-facing referral upload pathway disabled at Mr Wanigasooriya's request — the tool is clinician-use only. The patient form now displays "not in use" and the server rejects any such submission.

Structured discordance capture designed (approved by Mr Wanigasooriya): where the clinician's decision differs from the algorithm's recommendation, the reviewer records a reason (algorithm error / clinician deviation / transcription difference / clinically equivalent / other) and a direction — with clinician-recommended-less-than-algorithm flagged as potential under-investigation, the key safety signal.

First draft of the GEH Clinical Audit Proposal Form completed.

# 1 July 2026 — Data governance decision and go-live

Information-governance review of the data flow. Decision: the tool holds and transmits no patient data at all. It is a stateless calculator — the clinician enters a case, reads the recommendation, and copies a single spreadsheet row.

All audit data lives in one controlled-access Excel workbook inside the department's own Microsoft Teams (South Warwickshire NHS tenant) — the same in-tenant model already used for the department's M&M sheet and handover patient lists. MRN is permitted as case identifier because the data never leaves the Trust tenant.

An automated one-click submission flow (Power Automate) was assessed and rejected: any automated flow of patient-identifiable data would require IG assessment/DPIA; manual copy-paste into the Teams workbook keeps the tool at zero data transmission.

Final-diagnosis field added to the tool and workbook (colorectal cancer / other cancer / benign / not known) so cancer outcomes can be analysed against the algorithm's recommendations.

Audit workbook built and uploaded to the Teams channel: 38 columns matching the tool's copy-row exactly; a Guide sheet; and a Summary sheet with live formulas — overall concordance %, cancer counts, and a highlighted safety measure: cancers where the algorithm's recommendation would have meant less investigation than the clinician performed.

Teams channel "AI 2WW Project" set up inside the 2WW LGI Pathway team, with the tool link and workbook pinned.

Tool verified live: a test case marks correctly; the copied row matches the workbook's 38 columns; empty submissions are rejected.

Proposal form updated to reflect the local-Teams data-handling model and the cancer-outcome/safety aims — ready for clinical.audit@geh.nhs.uk.

# Current status (2 July 2026)

LIVE and collecting. Team members enter 2WW cases via the tool and paste rows into the workbook; final diagnoses are completed as outcomes become known (the channel's existing `Suspected_Diagnosed_Cancer_Report.xlsx` may serve as the outcome source — to be confirmed).

Nothing about the pathway itself has changed: the audit measures concordance retrospectively; clinical decisions remain entirely with the clinicians.

# Next steps

Case entry by the project team (target dataset size per proposal form).

Final-diagnosis column completed as outcomes mature.

Interim review of the Summary sheet (concordance % and the safety measure) with Mr Wanigasooriya.

Findings written up for presentation / publication.

This log is maintained by Ali Mohamed Elhassan (with AI-assisted development tooling). Last updated 2 July 2026.