# 2WW Colorectal Triage Aid — Build Record

A chronological record of how the tool was designed, built, verified and governed.

Prepared for Mr Kasun Wanigasooriya (project lead) and available to the GEH Clinical Audit & QI office / AI Committee.

Maintained by Ali Mohamed Elhassan · Last updated 15 July 2026 · Companion documents: Technical Factsheet (AI & Data Handling), Algorithm Overview, Audit Protocol, Project Log.

# 1. What was built

A web-based deterministic calculator encoding George Eliot Hospital's approved 2WW colorectal investigation algorithm as a fixed, testable decision tree, plus an audit entry page that lets a reviewer enter an anonymised case, see the algorithm's recommendation with its full reasoning path, record the clinician's actual decision, and copy one spreadsheet row into the department's controlled Teams workbook.

The tool contains no artificial intelligence at runtime. Identical inputs always produce identical outputs; every output is stamped with the algorithm version and shows the exact steps followed.

| Item | Value |
| --- | --- |
| Tool URL | https://ww-colerectal.web.app/audit/new |
| Algorithm version | GEH-2WW-COLORECTAL v0.4.0 |
| Automated tests | 95, all passing; the full suite runs before any deployment |
| Hosting | Firebase (Google), London region (europe-west2), project-owned |
| Data stored by the tool | None — stateless calculator; audit data lives only in the Trust Teams workbook |
| Source of clinical logic | The Trust's 2WW colorectal pathway document, encoded branch-by-branch (see Algorithm Overview) |
| Cost / vendor / licence | None — built in-house by the project team |

# 2. How it was built — chronology

| Date (2026) | What was done |
| --- | --- |
| 20 May | Project scaffolded. First encoding of the Trust 2WW algorithm (v0.1 → v0.2), including the iron-deficiency-anaemia priority rule. Automated end-to-end smoke test added from day one. |
| 20 May | v0.2.1 — six algorithm corrections found by self-audit against the Trust document, each captured as a permanent regression test. |
| 21 May | Concordance-audit module added (reviewer entry workflow + analysis dashboard). Governance documents drafted (audit protocol, reviewer guide, design document). |
| 24 May | v0.3.0 → v0.4.0 — "No rectal mass" sub-branch, Abnormal-CT branch, structured prior-bowel-surgery and bleeding-source fields, free-text scanner for clinically material phrases, CTVC <2y routing exception. Statistical dashboard brought in line with the protocol (Wilson 95% CIs, Cohen's kappa, confusion matrix, pre-specified subgroups, stop-criteria alert). Test suite grown to 86, then 95. |
| 25 May | Audit workflow v0.5 — cohort tracking, custom audit IDs, structured exclusion handling with denominator transparency. "FY1" renamed "Reviewer" throughout (audit open to any grade). |
| 28–29 Jun | Reviewed by Mr Wanigasooriya (consultant colorectal surgeon, project lead) — endorsed; team formed. At his request the patient-facing referral-upload pathway was disabled in code (server rejects such submissions). Structured discordance capture added, as he approved: on any mismatch the reviewer must record a reason and a safety direction, with "clinician did less than the tool" flagged as the potential under-investigation signal. Hosting moved to Firebase London under project ownership. |
| 1 Jul | Information-governance review of the data flow. Decision: the tool holds and transmits no patient data at all. All persistence removed from the workflow — the reviewer copies a single row into a controlled-access Excel workbook inside the department's Microsoft Teams (same in-tenant model as the department's M&M and handover sheets; MRN permitted as the case identifier because data never leaves the Trust tenant). An automated Power Automate submission flow was assessed and rejected to keep the tool at zero data transmission. Final-diagnosis field added so cancer outcomes can be analysed against recommendations. Audit workbook (38 columns, Guide sheet, live Summary sheet with concordance % and the cancer-safety measure) built and pinned in the "AI 2WW Project" Teams channel. |
| 2 Jul | Live and collecting. Tool verified end-to-end: test case marks correctly, copied row matches the workbook's 38 columns, incomplete entries are rejected. |
| 7 Jul | Clinical Audit office query about AI answered (Mr Wanigasooriya); Technical Factsheet prepared covering the AI and data-handling position. |

# 3. How correctness is assured

Explicit, versioned rules. The algorithm is code that mirrors the Trust document

branch-by-branch; the mapping is written out in the Algorithm Overview for clinical review. Nothing is inferred or learned.

95 automated tests. Every branch has test cases with expected outcomes

(including the historical corrections from self-audit, kept as regression tests). The full suite must pass before any deployment.

Traceable outputs. Every recommendation displays the path taken — each rule

fired, the evidence used, and the algorithm version — so any single case can be checked by hand against the Trust document.

Structured discordance capture. Where the clinician's actual decision differs

from the tool, the reviewer classifies why and in which safety direction, so algorithm errors surface quickly and under-investigation risk is flagged red.

Change control. Any change to clinical logic requires: consultant agreement,

a version bump, tests covering the change, and the full suite passing — then the change is recorded in the Project Log.

# 4. Role of AI in development

An AI coding assistant (Claude, by Anthropic — free of charge in the form used) was used during software development to help write the code, as such assistants are now routinely used in software engineering. The clinical logic came from the Trust's algorithm document and the clinical team's direction; the resulting code is deterministic, human-reviewed, version-controlled and covered by the test suite.

No AI runs in the deployed tool, and no patient data of any kind was used in or sent to any AI system at any stage.

# 5. Data-handling position (summary)

The tool stores and transmits nothing — no database behind the form; the

patient-upload pathway is disabled at server level.

Audit data exists only in the controlled-access workbook in the Trust's Teams

tenant; MRN stays inside Trust systems; nothing identifiable leaves them.

A pilot banner on every page states the tool is for audit use only and is not a

Trust-endorsed clinical decision support tool; recommendations are not used in patient care (the audit is retrospective).

*Full detail: Technical Factsheet (AI & Data Handling) · Algorithm Overview · Audit Protocol · Project Log. Source code, test suite and version history are available for inspection on request.*